## 전체일정
Puppy Playtime 프로젝트
[6 empty] | 공통작업 |  |  | 박찬영 |  |  | 조민의 |  |  | 김주현 |  |  | 허성경 |  |  | 최성호 |  |  | 김주영
분류 | 관리자/사용자 | 작업 분류 | 세부 작업 | 담당파트
[5 empty] | 1week |  |  |  |  | 2week | [6 empty] | 3week | [6 empty] | 4week | [6 empty] | 5week | [6 empty] | 6week | [6 empty] | 7week
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Project |  |  |  |  | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr
기획 / 개발준비 |  |  | 프로젝트 컨텐츠 선정 | bar: 1week 4 Sa; 2week 12 Su; 3week 19 Su; 5week 2 Su
자료조사, 요구사항 명세서 | bar: 4week 26 Su
개체관계도, 테이블 모델링, 테이블 명세서 | bar: 1week 1 We; 4week 26 Su
UseCaseDiagram | bar: 1week 2 Th; 4week 26 Su
사이트맵,Layout | bar: 1week 3 Fr; 4week 26 Su
스토리 보드 | bar: 4week 26 Su
구조명세서 작성 | bar: 4week 26 Su
일정관리 | bar: 3week 14 Tu to 3week 15 We; 4week 21 Tu to 4week 22 We; 4week 26 Su; 5week 28 Tu to 5week 29 We; 6week 4 Tu to 6week 5 We; 6week 9 Su; 7week 11 Tu to 7week 12 We
테이블 생성, 이미지자료 수집 | bar: 3week 15 We; 4week 21 Tu to 4week 22 We; 4week 26 Su; 5week 28 Tu to 5week 29 We; 6week 4 Tu to 6week 5 We; 6week 9 Su; 7week 11 Tu to 7week 12 We
개발 환경 구축 | bar: 3week 14 Tu to 3week 15 We; 4week 21 Tu to 4week 22 We; 4week 26 Su; 5week 28 Tu to 5week 29 We; 6week 4 Tu to 6week 5 We; 6week 9 Su; 7week 11 Tu to 7week 12 We
체크리스트 | bar: 2week 12 Su; 3week 19 Su; 5week 2 Su
구현 | 사용자 | 메인 | 배너 | bar: 4week 26 Su
메인 컨텐츠 | bar: 2week 12 Su; 4week 26 Su; 6week 6 Th
|  | 템플릿 | 타일즈 설정 | bar: 4week 26 Su; 6week 6 Th
템플릿 작업 | bar: 4week 26 Su; 6week 7 Fr; 7week 11 Tu to 7week 12 We
|  | 회원 | 회원가입 | bar: 4week 21 Tu to 4week 22 We; 4week 24 Fr to 5week 27 Mo; 5week 31 Fr to 5week 1 Sa; 6week 8 Sa; 7week 10 Mo
비밀번호 암호화 구현 | bar: 4week 25 Sa to 5week 27 Mo; 5week 1 Sa; 6week 8 Sa; 7week 10 Mo
이메일 인증 | bar: 4week 26 Su to 5week 27 Mo; 5week 1 Sa; 6week 8 Sa; 7week 10 Mo
정규식 구현 | bar: 4week 26 Su to 5week 27 Mo; 5week 1 Sa; 6week 8 Sa; 7week 10 Mo
아이디 찾기 | bar: 4week 25 Sa to 5week 27 Mo; 5week 1 Sa; 6week 8 Sa; 7week 10 Mo
비밀번호 찾기 | bar: 4week 25 Sa to 5week 27 Mo; 5week 1 Sa; 6week 8 Sa; 7week 10 Mo
세션 구현 | bar: 4week 25 Sa to 5week 27 Mo; 5week 30 Th to 5week 1 Sa; 6week 6 Th to 6week 8 Sa; 7week 10 Mo
|  | 마이페이지 | 내 정보 수정 | bar: 5week 2 Su; 6week 8 Sa; 7week 10 Mo
마이펫 관리 | bar: 4week 25 Sa to 5week 27 Mo; 5week 30 Th to 5week 1 Sa; 6week 8 Sa; 7week 10 Mo
이메일 인증 | bar: 4week 25 Sa to 5week 27 Mo; 5week 1 Sa; 6week 8 Sa; 7week 10 Mo
예약 관리 | bar: 4week 22 We; 5week 1 Sa; 6week 6 Th; 6week 9 Su to 7week 10 Mo
정규식 구현 | bar: 3week 19 Su; 5week 1 Sa; 6week 7 Fr to 6week 8 Sa; 7week 10 Mo
|  | 예약하기 | 예약날짜 입력 | bar: 3week 19 Su; 6week 9 Su to 7week 10 Mo
마이펫 선택 | bar: 3week 19 Su; 6week 9 Su to 7week 10 Mo
예약룸 리스트 | bar: 3week 19 Su; 5week 1 Sa; 6week 8 Sa; 7week 10 Mo to 7week 12 We
상세 예약 | bar: 3week 16 Th; 3week 19 Su to 4week 20 Mo; 4week 22 We; 5week 1 Sa; 6week 8 Sa; 7week 10 Mo; 7week 12 We to 7week 14 Fr
|  | 문의게시판 | 문의게시판 리스트 페이지 | bar: 3week 18 Sa; 4week 25 Sa; 5week 28 Tu to 5week 1 Sa; 6week 8 Sa
문의게시판 글쓰기 | bar: 3week 14 Tu to 3week 15 We; 3week 18 Sa; 5week 30 Th; 5week 1 Sa; 6week 7 Fr to 6week 8 Sa
댓글 확인 | bar: 3week 14 Tu to 3week 15 We; 3week 17 Fr to 3week 18 Sa; 4week 25 Sa; 5week 2 Su; 6week 8 Sa
당사자 외 문의내역 보기 제한 | bar: 6week 5 We; 6week 8 Sa
|  | 고객센터 | 공지사항 | bar: 1week 4 Sa to 1week 5 Su; 2week 12 Su to 3week 17 Fr; 6week 7 Fr
룸 소개 | bar: 2week 12 Su; 4week 21 Tu; 7week 10 Mo
이용 안내
| 관리자 | 메인 | 승인 전 예약 리스트 | bar: 3week 14 Tu to 3week 15 We; 3week 17 Fr to 3week 18 Sa; 4week 21 Tu to 4week 25 Sa; 5week 27 Mo to 5week 1 Sa; 6week 4 Tu to 6week 8 Sa; 7week 10 Mo to 7week 13 Th
금일 가입자 수 | bar: 3week 14 Tu to 3week 15 We; 3week 17 Fr to 3week 18 Sa; 4week 21 Tu to 5week 1 Sa; 6week 4 Tu to 6week 8 Sa; 7week 10 Mo to 7week 14 Fr
메뉴 작업 | bar: 3week 14 Tu to 3week 15 We; 3week 17 Fr to 3week 18 Sa; 4week 21 Tu to 5week 1 Sa; 6week 4 Tu to 6week 8 Sa; 7week 10 Mo to 7week 14 Fr
|  | 통계 | 월별 가입자 통계 | bar: 3week 18 Sa; 4week 22 We to 5week 30 Th; 5week 1 Sa; 6week 4 Tu; 6week 7 Fr to 6week 8 Sa; 7week 10 Mo to 7week 14 Fr
월별 예약 통계 | bar: 3week 16 Th; 3week 18 Sa; 4week 21 Tu; 4week 25 Sa to 4week 26 Su; 5week 28 Tu to 5week 30 Th; 6week 4 Tu; 6week 7 Fr to 6week 8 Sa; 7week 10 Mo to 7week 14 Fr
월별 매출 통계 | bar: 3week 18 Sa; 4week 21 Tu to 4week 26 Su; 5week 28 Tu; 5week 30 Th; 6week 7 Fr to 6week 8 Sa; 7week 10 Mo to 7week 14 Fr
|  | 애견공간 관리 | 룸 목록 | bar: 3week 18 Sa; 4week 21 Tu to 4week 26 Su; 6week 5 We to 6week 8 Sa; 7week 10 Mo to 7week 14 Fr
룸 등록 및 수정 | bar: 3week 18 Sa; 4week 21 Tu to 4week 26 Su; 5week 30 Th to 5week 1 Sa; 6week 4 Tu to 6week 5 We; 6week 7 Fr to 6week 8 Sa; 7week 10 Mo to 7week 14 Fr
룸 비활성화 | bar: 3week 14 Tu to 3week 15 We; 3week 18 Sa; 4week 21 Tu to 4week 26 Su; 5week 30 Th to 5week 1 Sa; 6week 6 Th; 6week 8 Sa; 7week 13 Th to 7week 14 Fr
|  | 부가서비스 관리 | 부가서비스 목록 | bar: 3week 14 Tu; 3week 18 Sa; 4week 21 Tu to 4week 23 Th; 4week 25 Sa to 4week 26 Su; 5week 30 Th; 5week 1 Sa; 6week 4 Tu to 6week 8 Sa; 7week 10 Mo to 7week 14 Fr
부가서비스 등록 | bar: 3week 14 Tu to 3week 18 Sa; 4week 21 Tu to 4week 23 Th; 4week 25 Sa to 4week 26 Su; 6week 4 Tu to 6week 8 Sa; 7week 10 Mo to 7week 14 Fr
갱신여부 메일발송 | bar: 3week 14 Tu to 3week 16 Th; 3week 18 Sa; 4week 21 Tu; 4week 23 Th to 5week 1 Sa; 6week 4 Tu to 6week 8 Sa; 7week 10 Mo to 7week 14 Fr
|  | 예약관리 | 예약 리스트 | bar: 3week 14 Tu to 3week 16 Th; 3week 18 Sa; 4week 24 Fr to 5week 1 Sa; 6week 4 Tu to 6week 8 Sa; 7week 10 Mo to 7week 14 Fr
예약 승인 및 승인거부 | bar: 3week 14 Tu to 3week 18 Sa; 4week 21 Tu to 4week 23 Th; 4week 25 Sa to 5week 27 Mo; 5week 30 Th to 5week 1 Sa; 6week 6 Th to 6week 8 Sa; 7week 10 Mo to 7week 14 Fr
예약 취소 | bar: 3week 14 Tu to 3week 18 Sa; 4week 21 Tu to 4week 23 Th; 4week 25 Sa to 5week 27 Mo; 5week 30 Th to 5week 1 Sa; 6week 4 Tu; 6week 6 Th to 6week 8 Sa; 7week 10 Mo to 7week 14 Fr
|  | 회원관리 | 회원 리스트 | bar: 3week 14 Tu to 3week 18 Sa; 5week 31 Fr to 5week 1 Sa; 6week 4 Tu to 6week 8 Sa; 7week 10 Mo to 7week 14 Fr
회원 상세정보 | bar: 3week 14 Tu to 3week 18 Sa; 6week 4 Tu to 6week 8 Sa; 7week 10 Mo to 7week 14 Fr
|  | 회원관리 | 회원 비활성화 | bar: 3week 14 Tu to 3week 18 Sa; 5week 29 We to 5week 1 Sa; 6week 6 Th to 6week 8 Sa; 7week 10 Mo to 7week 14 Fr
|  | 공지사항관리 | 공지사항 쓰기 | bar: 3week 14 Tu to 3week 17 Fr; 5week 29 We to 5week 1 Sa; 6week 4 Tu to 6week 5 We; 6week 7 Fr to 6week 8 Sa; 7week 10 Mo to 7week 14 Fr
공지사항 수정 | bar: 3week 14 Tu to 3week 18 Sa; 5week 29 We to 5week 1 Sa; 6week 4 Tu to 6week 6 Th; 6week 8 Sa; 7week 10 Mo to 7week 14 Fr
공지사항 삭제 | bar: 3week 14 Tu to 3week 18 Sa; 5week 29 We to 5week 1 Sa; 6week 4 Tu to 6week 6 Th; 6week 8 Sa; 7week 10 Mo to 7week 14 Fr
|  | 문의게시판관리 | 문의게시판 리스트 | bar: 3week 14 Tu to 3week 18 Sa; 6week 4 Tu to 6week 8 Sa; 7week 10 Mo to 7week 14 Fr
문의글 상세 페이지 | bar: 3week 14 Tu to 3week 18 Sa; 6week 4 Tu to 6week 8 Sa; 7week 10 Mo to 7week 14 Fr
답변 등록 | bar: 3week 14 Tu to 3week 18 Sa; 6week 5 We to 6week 8 Sa; 7week 10 Mo to 7week 14 Fr
답변 수정 | bar: 5week 30 Th to 5week 2 Su; 6week 5 We; 7week 10 Mo
테스트 |  |  | 단위테스트 | 박찬영 | bar: 1week 4 Sa; 2week 6 Mo; 3week 14 Tu to 3week 18 Sa; 4week 21 Tu to 4week 24 Fr; 5week 27 Mo to 5week 31 Fr; 6week 4 Tu to 6week 7 Fr; 7week 10 Mo to 7week 13 Th
조민의 | bar: 3week 14 Tu to 3week 18 Sa; 4week 21 Tu to 4week 24 Fr; 4week 26 Su to 5week 31 Fr; 6week 4 Tu to 6week 7 Fr; 7week 10 Mo to 7week 14 Fr
김주현 | bar: 3week 14 Tu to 3week 18 Sa; 4week 21 Tu to 4week 24 Fr; 4week 26 Su to 5week 31 Fr; 6week 4 Tu to 6week 7 Fr; 7week 10 Mo to 7week 14 Fr
허성경 | bar: 3week 14 Tu to 3week 18 Sa; 4week 21 Tu to 4week 24 Fr; 4week 26 Su to 5week 31 Fr; 6week 4 Tu to 6week 7 Fr; 7week 10 Mo to 7week 14 Fr
최성호 | bar: 3week 14 Tu to 3week 18 Sa; 4week 21 Tu to 4week 24 Fr; 4week 26 Su to 5week 31 Fr; 6week 4 Tu to 6week 7 Fr; 7week 10 Mo to 7week 14 Fr
김주영 | bar: 3week 14 Tu to 3week 18 Sa; 4week 21 Tu to 4week 24 Fr; 4week 26 Su to 5week 31 Fr; 6week 4 Tu to 6week 7 Fr; 7week 10 Mo to 7week 14 Fr
통합 및 테스트 | bar: 3week 14 Tu to 3week 16 Th; 7week 10 Mo
시범운영 | bar: 1week 4 Sa; 5week 27 Mo; 7week 10 Mo